## Bake WBS
ID | Task | Hours | Est. Days | Complexity | Role
1 · INITIATION & ARCHITECTURE
1.1 | Project kick-off, stakeholder alignment & scope sign-off | 24 | 3 | Low | PM
1.2 | Current-state VBA & SAP integration analysis | 40 | 5 | Medium | SA
1.3 | Solution architecture design (React + .NET + SAP RFC layer) | 40 | 5 | High | SA
1.4 | Tech stack decisions, repo setup, CI/CD pipeline skeleton | 24 | 3 | Medium | DevOps
1.5 | Database design (bake log, sand trans, reference data, audit) | 32 | 4 | Medium | BA / Dev
1.6 | API contract definition (OpenAPI / Swagger spec) | 24 | 3 | Medium | SA
1.7 | UI/UX wireframes & prototype review (3 screens) | 40 | 5 | Medium | UI/UX
1.8 | Sprint planning & backlog grooming | 16 | 2 | Low | PM
2 · BACKEND — .NET API
2.1 | Project scaffolding (.NET 8 Web API, EF Core, solution structure) | 16 | 2 | Low | Dev BE
2.2 | Authentication & authorisation (Windows AD / LDAP integration) | 40 | 5 | High | Dev BE
2.3 | Reference data API (ovens, hampers, defect codes, printers, yield rates) | 32 | 4 | Medium | Dev BE
2.4 | Bake record CRUD API (create, read, update, SAP-flag management) | 48 | 6 | Medium | Dev BE
2.5 | Sand transfer CRUD API | 32 | 4 | Medium | Dev BE
2.6 | Offline queue service (store-and-forward when SAP unavailable) | 48 | 6 | High | Dev BE
2.7 | Audit log & event sourcing (replaces LogEvent CSV) | 32 | 4 | Medium | Dev BE
2.8 | Remote backup service (replaces OvenLog.xlsx sync) | 24 | 3 | Medium | Dev BE
2.9 | Label print API (wraps SAP ZPPLLABEL / network printer) | 32 | 4 | Medium | Dev BE
2.1 | Ketchup (SAP replay) background service | 40 | 5 | High | Dev BE
2.11 | Unit tests — backend (≥80% coverage target) | 40 | 5 | Medium | Dev BE
2.12 | API documentation & Swagger finalisation | 16 | 2 | Low | Dev BE
3 · FRONTEND — REACT
3.1 | React project setup (Vite, TypeScript, component library, routing) | 16 | 2 | Low | Dev FE
3.2 | Design system / shared components (form fields, badges, tables, toasts) | 40 | 5 | Medium | Dev FE
3.3 | BakeForm screen — Serialized (all 13 fields, toggle buttons, SAP lookups) | 64 | 8 | High | Dev FE
3.4 | BakeForm screen — Non-Serialized (12 fields, scrap code, label print) | 48 | 6 | High | Dev FE
3.5 | SandForm screen (MB52 stock display, FIFO indicator, transfer flow) | 40 | 5 | Medium | Dev FE
3.6 | Bake Log view (filterable table, SAP flag status, pagination) | 32 | 4 | Medium | Dev FE
3.7 | Reference data admin screen (hampers, printers, oven map, defect codes) | 32 | 4 | Medium | Dev FE
3.8 | Online / offline mode indicator & queue status panel | 24 | 3 | Medium | Dev FE
3.9 | Label print flow (label count, qty per label, printer selector) | 24 | 3 | Low | Dev FE
3.1 | Material spec viewer (OD/ID/wall display from SAP MM03) | 24 | 3 | Medium | Dev FE
3.11 | Responsive layout & accessibility (keyboard nav, screen reader) | 24 | 3 | Medium | Dev FE
3.12 | Unit & component tests (React Testing Library, ≥70% coverage) | 40 | 5 | Medium | Dev FE
4 · SAP INTEGRATION LAYER
4.1 | SAP RFC/BAPI connectivity setup (.NET SAP Connector / NCo 3.x) | 32 | 4 | High | Dev SAP
4.2 | COR3 — Process order lookup service | 32 | 4 | Medium | Dev SAP
4.3 | MM03 — Material description & spec retrieval service | 32 | 4 | Medium | Dev SAP
4.4 | COR6 — Step 20 & Step 40 confirmation posting service | 64 | 8 | High | Dev SAP
4.5 | MIGO — Goods movement posting (261, 309) service | 48 | 6 | High | Dev SAP
4.6 | MB52 — Warehouse stock query service | 32 | 4 | Medium | Dev SAP
4.7 | MB51 — Material document FIFO lookup service | 32 | 4 | Medium | Dev SAP
4.8 | ZMMS2S — Custom sand transfer transaction service | 40 | 5 | High | Dev SAP
4.9 | COP1 / COWBHU — Handling unit creation service | 48 | 6 | High | Dev SAP
4.1 | SAP error handling, retry logic & COGI fallback | 40 | 5 | High | Dev SAP
4.11 | SAP integration tests (sandbox environment) | 48 | 6 | High | Dev SAP
5 · DATA MIGRATION
5.1 | Data profiling — Sheet1, SandTrans, Sheet2 reference tables | 24 | 3 | Medium | BA
5.2 | Migration scripts — historical bake log (1,650+ rows → DB) | 32 | 4 | Medium | Dev BE
5.3 | Migration scripts — sand transfer log (147 rows → DB) | 16 | 2 | Low | Dev BE
5.4 | Reference data seed scripts (hampers, ovens, printers, defect codes) | 16 | 2 | Low | Dev BE
5.5 | Migration dry-run & data validation (row counts, SAP flag reconcile) | 24 | 3 | Medium | BA / QA
5.6 | Cut-over migration plan & rollback procedure | 16 | 2 | Medium | PM / BA
6 · TESTING & QA
6.1 | Integration test plan authoring | 24 | 3 | Medium | QA
6.2 | End-to-end test cases — bake recording (serialized path) | 40 | 5 | High | QA
6.3 | End-to-end test cases — bake recording (non-serialized path) | 32 | 4 | High | QA
6.4 | End-to-end test cases — sand transfer | 24 | 3 | Medium | QA
6.5 | SAP sandbox regression testing (all 9 transactions) | 48 | 6 | High | QA / Dev SAP
6.6 | Offline mode & queue replay testing | 32 | 4 | High | QA
6.7 | Performance testing (API response times, concurrent users) | 24 | 3 | Medium | QA
6.8 | UAT — operator walkthrough (2 shifts, 3 furnace operators) | 40 | 5 | Medium | BA / PM
6.9 | UAT defect triage & fix | 40 | 5 | High | Dev BE / FE
6.1 | Security review (auth, input validation, no hardcoded paths) | 24 | 3 | Medium | SA / Dev BE
7 · DEPLOYMENT & HANDOVER
7.1 | Production environment setup (IIS / Azure App Service, DB, networking) | 24 | 3 | Medium | DevOps
7.2 | CI/CD pipeline — build, test, deploy (GitHub Actions / Azure DevOps) | 24 | 3 | Medium | DevOps
7.3 | Monitoring & alerting setup (App Insights / health checks) | 16 | 2 | Medium | DevOps
7.4 | Operator training (hands-on session, 2-hour workshop × 2 groups) | 24 | 3 | Low | PM / BA
7.5 | User documentation & quick-reference card | 16 | 2 | Low | BA
7.6 | Parallel run — new app + VBA side-by-side (2-week overlap) | 80 | 10 | High | PM / All
7.7 | Production cut-over & VBA decommission | 16 | 2 | Medium | PM / DevOps
7.8 | Post-go-live hypercare (2 weeks on-call support) | 80 | 10 | Medium | Dev BE / FE
7.9 | Project closure — lessons learned, final documentation | 16 | 2 | Low | PM
| Total | 2248 | 281 | 56.2