## HVPackWBS
ID | Task | Hours | Est. Days | Complexity | Role
1. INITIATION & ARCHITECTURE
1.1 | Project kick-off; stakeholder meeting; scope sign-off | 18 | 3 | Low | PM
1.2 | Current-state analysis (manual HVPack processes; SAP integration) | 30 | 4 | Medium | SA
1.3 | Solution architecture (UI stack; .NET backend; SAP BTP integration) | 32 | 4 | High | SA
1.4 | Tech stack & infra setup (repo; CI/CD; DB; printers integration) | 18 | 3 | Medium | DevOps
1.5 | Database/schema design (hamper log; batch; ref data; audit) | 24 | 3 | Medium | BA / Dev
1.6 | API contract definition & review (OpenAPI/Swagger) | 16 | 2 | Medium | SA
1.7 | UI/UX wireframes & prototype review (core screens; print flows) | 28 | 4 | Medium | UI/UX
1.8 | Sprint planning & backlog grooming | 12 | 2 | Low | PM
2. BACKEND .NET API
2.1 | Project scaffolding (.NET Web API; EF Core; repo pattern) | 12 | 2 | Low | Dev BE
2.2 | Authentication & authorisation (AD / LDAP) | 24 | 3 | High | Dev BE
2.3 | Reference data API (hampers; batches; printers; defect codes; rates) | 22 | 3 | Medium | Dev BE
2.4 | Hamper record CRUD API (create/read/update/SAP-flag mgmt) | 36 | 5 | Medium | Dev BE
2.5 | Batch & pack CRUD API | 22 | 3 | Medium | Dev BE
2.6 | Offline queue processor (store & forward when SAP unavailable) | 36 | 5 | High | Dev BE
2.7 | Audit log & event sourcing | 22 | 3 | Medium | Dev BE
2.8 | Remote backup service | 16 | 2 | Medium | Dev BE
2.9 | Label print API (templates; BTP print relay) | 22 | 3 | Medium | Dev BE
2.1 | SAP replay background service | 28 | 4 | High | Dev BE
2.11 | Unit tests â€” backend (â‰¥80% coverage) | 28 | 4 | Medium | Dev BE
2.12 | API documentation & Swagger finalisation | 12 | 2 | Low | Dev BE
3. FRONTEND UI
3.1 | UI project setup (stack | 12 | 2 | Low | Dev FE
3.2 | Shared UI components (fields; tables; badges; toasts) | 28 | 4 | Medium | Dev FE
3.3 | Hamper Entry screen (all input; toggle; SAP lookups) | 44 | 6 | High | Dev FE
3.4 | Batch Entry & Pack screen (quantity target | 28 | 4 | Medium | Dev FE
3.5 | Hamper Log view (filterable; print queue status; pagination) | 24 | 3 | Medium | Dev FE
3.6 | Reference admin screen | 24 | 3 | Medium | Dev FE
3.7 | Online/offline mode indicator & queue status | 16 | 2 | Medium | Dev FE
3.8 | Label print flow (count; qty per label; printer selection) | 16 | 2 | Low | Dev FE
3.9 | Material spec & packaging chart viewer | 16 | 2 | Medium | Dev FE
3.1 | UX accessibility & responsive layout | 16 | 2 | Medium | Dev FE
3.11 | Unit & component tests (â‰¥70% coverage) | 28 | 4 | Medium | Dev FE
4. SAP INTEGRATION LAYER
4.1 | SAP BTP API connectivity setup | 22 | 3 | High | Dev SAP
4.2 | Order lookup (COR3) integration | 22 | 3 | Medium | Dev SAP
4.3 | Material spec query (MM03) | 22 | 3 | Medium | Dev SAP
4.4 | Confirmation post (COR6) integration | 44 | 6 | High | Dev SAP
4.5 | Hamper post (MIGO/Custom) | 28 | 4 | High | Dev SAP
4.6 | Warehouse stock (MB52) query | 22 | 3 | Medium | Dev SAP
4.7 | Hamper trace FIFO lookup | 22 | 3 | Medium | Dev SAP
4.8 | Label print integration (BTP relay) | 24 | 3 | High | Dev SAP
4.9 | SAP error handling & retry/COGI fallbacks | 24 | 3 | High | Dev SAP
4.1 | Integration tests (SAP sandbox) | 28 | 4 | High | Dev SAP
5. DATA MIGRATION
5.1 | Data profiling (legacy hampers; batches; ref tables) | 16 | 2 | Medium | BA
5.2 | Migrate hamper log | 22 | 3 | Medium | Dev BE
5.3 | Migrate batch log | 10 | 2 | Low | Dev BE
5.4 | Reference data seeding | 10 | 2 | Low | Dev BE
5.5 | Dry-run; validation; cut-over planning | 16 | 2 | Medium | BA / QA
5.6 | Rollback procedure | 10 | 2 | Medium | PM / BA
6. TESTING & QA
6.1 | Test plan authoring | 16 | 2 | Medium | QA
6.2 | E2E test cases â€” pack/hamper flow | 28 | 4 | High | QA
6.3 | E2E test cases â€” batch flow | 22 | 3 | High | QA
6.4 | Integration testing (SAP; offline mode) | 28 | 4 | High | QA / Dev SAP
6.5 | Performance testing | 16 | 2 | Medium | QA
6.6 | UAT (2+ shifts) | 24 | 3 | Medium | BA / PM
6.7 | UAT defect triage & fix | 24 | 3 | High | Dev BE / FE
6.8 | Security review | 16 | 2 | Medium | SA / Dev BE
7. DEPLOYMENT & HANDOVER
7.1 | Prod environment setup | 16 | 2 | Medium | DevOps
7.2 | CI/CD pipeline | 14 | 2 | Medium | DevOps
7.3 | Monitoring & alerting | 10 | 2 | Medium | DevOps
7.4 | Operator training | 14 | 2 | Low | PM / BA
7.5 | Documentation | 10 | 2 | Low | BA
7.6 | Parallel run (old+new app) | 48 | 6 | High | PM / All
7.7 | Cut-over & decommission | 10 | 2 | Medium | PM / DevOps
7.8 | Hypercare (2 weeks) | 48 | 6 | Medium | Dev BE / FE
7.9 | Project closure | 10 | 2 | Low | PM