## SerializedWBS
ID | Task | Hours | Est. Days | Complexity | Role
1. INITIATION & ARCHITECTURE
1.1 | Project kick-off; stakeholder alignment & scope sign-off | 20 | 3 | Low | PM
1.2 | Current-state analysis (manual serialization processes; SAP integration) | 32 | 4 | Medium | SA
1.3 | Solution architecture (UI stack; .NET backend; SAP BTP integration) | 36 | 5 | High | SA
1.4 | Tech stack & infrastructure setup (repo; CI/CD; DB provisioning) | 20 | 3 | Medium | DevOps
1.5 | Database/schema design (serial log; defect; ref data; audit) | 28 | 4 | Medium | BA / Dev
1.6 | API contract definition & review (OpenAPI/Swagger) | 20 | 3 | Medium | SA
1.7 | UI/UX wireframes & prototype review (main screens) | 36 | 5 | Medium | UI/UX
1.8 | Sprint planning & backlog grooming | 14 | 2 | Low | PM
2. BACKEND .NET API
2.1 | Project scaffolding (.NET Web API; EF Core; repository pattern) | 14 | 2 | Low | Dev BE
2.2 | Authentication & authorisation (AD / LDAP integration) | 34 | 5 | High | Dev BE
2.3 | Reference API (serials; defect codes; printers; yield rates) | 28 | 4 | Medium | Dev BE
2.4 | Serial entry CRUD API (create/read/update/SAP-flag management) | 44 | 6 | Medium | Dev BE
2.5 | Defect log CRUD API | 28 | 4 | Medium | Dev BE
2.6 | Offline queue processor (store & forward when SAP unavailable) | 44 | 6 | High | Dev BE
2.7 | Audit log & event sourcing | 28 | 4 | Medium | Dev BE
2.8 | Remote backup service | 20 | 3 | Medium | Dev BE
2.9 | Label print API (single format; BTP print relay) | 28 | 4 | Medium | Dev BE
2.1 | SAP replay background service | 36 | 5 | High | Dev BE
2.11 | Unit tests backend (test coverage) | 36 | 5 | Medium | Dev BE
2.12 | API documentation & Swagger finalisation | 14 | 2 | Low | Dev BE
3. FRONTEND UI
3.1 | UI project setup (stack; routing) | 14 | 2 | Low | Dev FE
3.2 | Shared UI components (fields; tables; badges; toasts) | 34 | 5 | Medium | Dev FE
3.3 | Serial Entry screen (all input fields; toggle buttons; SAP lookups) | 54 | 7 | High | Dev FE
3.4 | Defect Log screen (entry; review; close-out) | 32 | 4 | Medium | Dev FE
3.5 | Serial Log view (filterable table; SAP flag; pagination) | 28 | 4 | Medium | Dev FE
3.6 | Reference admin screen | 28 | 4 | Medium | Dev FE
3.7 | Online/offline mode indicator & queue status | 20 | 3 | Medium | Dev FE
3.8 | Label print flow (count; qty per label; printer select) | 20 | 3 | Low | Dev FE
3.9 | Material spec viewer (SAP MM03) | 20 | 3 | Medium | Dev FE
3.1 | UX accessibility & responsive layout | 20 | 3 | Medium | Dev FE
3.11 | Unit & component tests (â‰¥70% coverage) | 34 | 5 | Medium | Dev FE
4. SAP INTEGRATION LAYER
4.1 | SAP BTP API connectivity setup | 28 | 4 | High | Dev SAP
4.2 | Order lookup (COR3) integration | 28 | 4 | Medium | Dev SAP
4.3 | Material spec query (MM03) | 28 | 4 | Medium | Dev SAP
4.4 | Confirmation post (COR6) integration | 54 | 7 | High | Dev SAP
4.5 | Defect post (COR3/Custom) | 36 | 5 | High | Dev SAP
4.6 | Warehouse stock (MB52) query | 28 | 4 | Medium | Dev SAP
4.7 | Serial trace FIFO lookup | 28 | 4 | Medium | Dev SAP
4.8 | Label print integration (BTP relay) | 34 | 5 | High | Dev SAP
4.9 | SAP error handling & retry/COGI fallbacks | 34 | 5 | High | Dev SAP
4.1 | Integration tests (SAP sandbox) | 36 | 5 | High | Dev SAP
5. DATA MIGRATION
5.1 | Data profiling (legacy serial log; defect log; ref tables) | 20 | 3 | Medium | BA
5.2 | Migrate serial log | 28 | 4 | Medium | Dev BE
5.3 | Migrate defect log | 14 | 2 | Low | Dev BE
5.4 | Reference data seeding | 14 | 2 | Low | Dev BE
5.5 | Dry-run; validation; cut-over planning | 20 | 3 | Medium | BA / QA
5.6 | Rollback procedure | 12 | 2 | Medium | PM / BA
6. TESTING & QA
6.1 | Test plan authoring | 20 | 3 | Medium | QA
6.2 | E2E test cases â€” serialization path | 34 | 5 | High | QA
6.3 | E2E test cases â€” defect log | 28 | 4 | High | QA
6.4 | Integration testing (SAP; offline mode) | 36 | 5 | High | QA / Dev SAP
6.5 | Performance testing | 20 | 3 | Medium | QA
6.6 | UAT (2 shifts) | 32 | 4 | Medium | BA / PM
6.7 | UAT defect triage & fix | 32 | 4 | High | Dev BE / FE
6.8 | Security review | 20 | 3 | Medium | SA / Dev BE
7. DEPLOYMENT & HANDOVER
7.1 | Prod environment setup | 20 | 3 | Medium | DevOps
7.2 | CI/CD pipeline | 18 | 2 | Medium | DevOps
7.3 | Monitoring & alerting | 14 | 2 | Medium | DevOps
7.4 | Operator training | 18 | 3 | Low | PM / BA
7.5 | Documentation | 14 | 2 | Low | BA
7.6 | Parallel run (old+new app) | 64 | 8 | High | PM / All
7.7 | Cut-over & decommission | 14 | 2 | Medium | PM / DevOps
7.8 | Hypercare (2 weeks) | 64 | 8 | Medium | Dev BE / FE
7.9 | Project closure | 14 | 2 | Low | PM
| Total | 1768
221
44.2
11.05